## Sheet1
EXAMPLE
Timing | Activities | Resources | Funding sought | Applicant contribution | Total cost
Month and year | List the main activities that will lead to successful completion of your project in the order they will happen | List the resources required to complete the activity | (DCC contribution) excl. GST Physical goods or contractor services | (excl. GST) Physical goods, contractor services, labour, vehicle costs | excl. GST
March 2019 | Spray gorse | Contractor (Name of contractor) | 500 | 500 | 1000
June 2019 | Purchase plants | 500 trees and plant protectors | 3000 | 0 | 3000
July 2019 | Plant trees | Labour (160 hours @$20.55/hr) (e.g. 2 people, 10 days = 20 working days ) | 0 | 3288 | 3288
Total project cost and funding requested excl. GST |  |  | 3500 | 3788 | 7288
Timing | Activities | Resources | Funding sought | Applicant contribution | Total cost
Month and year | List the main activities that will lead to successful completion of your project in the order they will happen | List the resources required to complete the activity | (DCC contribution) excl. GST Physical goods or contractor services | (excl. GST) Physical goods, contractor services, labour, vehicle costs | excl. GST
Total project cost and funding requested excl. GST |  |  | 0 | 0 | 0